## Programmer Name
List of Development Team with Their Track
Emp No | Name | Designation
245 | Mohammad Hossain | Senior Programmer(Java)
244 | Shahinur Parvin | Senior Programmer(Oracle)
246 | Mizanur Rahman | Programmer(.Net)
247 | Shabbir Ahamed | Jr. Programmer(Oracle)
249 | Shaikat Hasan Khan | Senior Programmer(.Net)
252 | Shahanaz Sultana | Jr. Programmer(.Net)
256 | Shimul Akter | Jr. Programmer(.Net)
265 | Md. Masum Mia | Jr. Programmer(.Net)
276 | Ruhul Amin | Jr. Programmer(.Net)
279 | Abu Bakkar Siddique | Jr. Programmer(Java)
282 | Rubana Karim | Jr. Programmer(.Net)

## Development Time Frame
June 2014 Application Development Time Frame with related task
Task ID # | Task Short Desc | Priority | Assign Emp no | Start Date | End Date | No of Working Days | Status | Hold Start Date | Hold End Date
1 | Celldyn Ruby Bug fixing & configure | 1 | 245 | 18/06/2014 | 24/06/2014 | 5 | GREEN
2 | Support To LIS team | 1 | 245 | 17/06/2014 | 17/06/2014 | 1 | GREEN
3 | Celldyn Ruby UI | 2 | 245 | 16/06/2015 | 26/06/2014 | 1 | Yellow | 22/06/2014 | 24/06/2014
4 | serial Port bug issue logging | 3 | 245 | 15/06/2014 | 27/06/2014 | 1 | Yellow | 16/06/2014 | 23/06/2014
5 | support to implement web sms | 3 | 245 | 2014-11-06 | 2014-12-06 | 1 | GREEN
6 | LIS Document study for BSMMU | 3 | 245 | 2014-10-06 | 15/06/2014 | 2 | Orange

## Status,Priority,Project Desc
Priority |  |  | Color Code STATUS |  | Project
3 | Normal | 1 | GREEN | Completed | 1 | BillSoft
2 | Urgent | 2 | Yellow | On Going | 2 | Weblab
1 | Top Urgent | 3 | RED | InComplete | 3 | BillSoft Plus
|  | 4 | Orange | HOLD | 4 | Rufaida
[5 empty] | 5 | HL7
[5 empty] | 6 | LIS Integration
[5 empty] | 7 | C-Lab
[5 empty] | 8 | BSMMU
[5 empty] | 9 | COC

## TASK ID DEFINATION
Task ID according to Project Code
Project Code | Task ID # | Analysys/mail date | Task Defination according to mail / analysis
6 | 1 | 24/06/014 | Celldyn ruby program had some configuration issues and data insertion problem. We fixed the | We fixed | serial port configuration, testing for data insertion
6 | 2 | 17/06/2014 | configure remote ksmc pc for serial port comminucation , support and chat with Deveopment team, upload updated jar and testing
6 | 3 | 16/06/2015 | develop an UI for serial port program libray configuration , create an wizard for testing pc configuration for serial port communication, data validation
6 | 4 | 15/06/2014 | All exception ,error and bug has to be logged in a file for futher fast solution for serial port comminucation
7 | 5 | 2014-11-06 | web sms api implemetion and configuration for C-Lab
8 | 6 | 2014-10-06 | study document on LAB implementaion for different analyzer